MEDT 6462 – Grant Proposal – Part 3

Kristen Honaker

October 12, 2009

Grant Activities

The mission of our grant is to provide students with resources in the computer lab that will allow them to expressive creativity while demonstrating concepts learned in academic subjects and earning credit in their academic classes. In addition students will use technology projects to raise funds for future activities. Research has shown that students’ motivation levels are increased when they are allowed to incorporate technology in the classroom (Bracewell, Breuleux, Laferriere, Beniot, & Abdous, 1998). As motivation increases, so will student learning. Here are the activities we will be doing in order to reach our goals:

- Students will spend two to three class periods each week incorporating academic subjects into their computer lessons and will receive credit in corresponding academic class. Students will be encouraged to brainstorm and have input on the project format.

- Students will work in teams to create at least 15 educational posters on current studies in math, science, and reading/language arts. Ms. Hayes, the middle school teachers, and I will meet to discuss what standards should be assigned to the students. Academic standards will be referenced on each poster.

- Students will work in teams to create at least 5 informative and educational slide shows using PowerPoint. Students will incorporate digital photos and video in each slide show. Ms. Hayes, the middle school teachers, and I will meet to discuss what standards should be assigned to the students. Academic standards will be referenced in each slide show.

- Students will create magnets and posters to be used as a fundraiser. Magnets with quotes and popular sayings will be produced as well as posters and candid photos that may be purchased by staff, students, and parents. Fundraisers will be held in February and in May. February fundraiser will relate to Valentine’s Day. Products may also be personalized for specific purchasers.

REFERENCES

Bracewell, R., Breuleux, A., Laferriere, T., Beniot, J., & Abdous, M. (1998). The emerging contribution of online resources and tools to classroom learning and teaching. Montreal: Universite Laval. Retrieved October 12, 2009 from http://www.tact.fse.ulaval.ca/ang/html/review98.html.

Timeline

| ACTIVITY | TIMELINE | PERSON(S) RESPONSIBLE |
| --- | --- | --- |
| Pre-grant survey for teachers and students. | Jan. 5, 2010 | ITC |
| Determine academic standards to be covered in computer class. | Jan. 5, 2010 | ITC, middle school academic teachers, computer teacher |
| Students create 15-20 posters displaying current academic concepts. | -ongoing- Jan. 11-May 18, 2010 | Students, computer teacher |
| Fundraiser Planning Meeting #1 | Jan. 20, 2010 | ITC, computer teacher |
| Posters displayed throughout hallway. | Feb. 1, 2010 | Students, computer teacher |
| Students create posters and magnets for fundraiser. | Jan. 27-Feb. 11, 2010 | Students, computer teacher |
| Distribute fundraiser projects. | Feb. 12, 2010 | Students, computer teacher |
| Calculate fundraiser profit. | Feb. 17, 2010 | ITC, computer teacher |
| Share fundraiser total with class/staff over intercom. | Feb. 18, 2010 | Computer teacher |
| Students create 2-3 slide shows displaying current academic concepts. | -ongoing- Feb 25-May 25, 2010 | Students, computer teacher |
| Slide shows shown through TV distribution system. | Mar. 8, 2010 | Computer teacher, media specialist |
| Student and teacher formative surveys on grant activities. | Mar. 8, 2010 | ITC, students, teachers |
| Determine 2nd set of academic standards to be covered in computer class. Adjust strategies if needed according to survey results. | Mar. 9, 2010 | ITC, middle school academic teachers, computer teacher |
| Display new set of student created posters in the hallway. | Mar. 25, 2010 | Students, computer teacher |
| New set of slide shows shown through TV distribution system. | Apr. 19, 2010 | Computer teacher, media specialist |
| Fundraiser Planning Meeting #2 | Apr. 20, 2010 | ITC, computer teacher |
| Students create posters and magnets for fundraiser. | Apr. 26 – May 6, 2010 | Students, computer teacher |
| Calculate fundraiser totals. | May 7, 2010 | ITC, computer teacher |
| Share with class/staff over intercom. | May 10, 2010 | Computer teacher |
| ACTIVITY | TIMELINE | PERSON(S) RESPONSIBLE |
| Student and teacher summative surveys on grant activities. | May 26 2010 | ITC, students, teachers |
| Data collection on class averages. | June 1, 2010 | ITC, middle school teachers |
| Grant impact information (survey results, fundraiser totals, student averages) will be disseminated via slide show at last faculty meeting. | June 3, 2010 | ITC |
| Grant impact information (survey results, fundraiser totals, student averages) will be disseminated to Kids In Need Foundation via report. | June 10, 2010 | ITC |

Evaluation

Our grant will be evaluated by the instructional technology coordinator and the computer teacher. The tables below detail the outcomes, data collection method, and dates of evaluation. We will base our success on increases in student averages, increases in student interest, and fundraiser earnings.

| Goal #1: Provide students with additional classroom time devoted to academic subject areas. |  |  |
| --- | --- | --- |
| Outcome | Data Collection | Date(s) |
| Students will spend two to three class periods a week working on academic topics in computer class. | ITC receives a copy of weekly lesson plans from computer teacher. | Weekly starting January 11 |

| Goal #2: Increase student interest and motivation in the classroom by allowing them to create products. |  |  |
| --- | --- | --- |
| Outcome | Data Collection | Date(s) |
| The number of students who consider themselves to be motivated will increase by 50%. | Pre-grant survey Formative survey Summative survey | Jan. 5, 2010 March 8, 2010 March 26, 2010 |

| Goal #3: Provide students an opportunity to use a combination of technology skills and individual creativity to produce academic based projects that they will receive credit for in their academic classes. |  |  |
| --- | --- | --- |
| Outcome | Data Collection | Date(s) |
| Students will earn 1-5 points on their overall academic averages through projects created in computer class. | ITC and middle school teachers calculate student averages with and without extra credit from computer projects. | June 1, 2010 |
| Goal #4: Utilize student computer skills for fundraisers that will allow the school to keep the projects going for many years to come. |  |  |
| Outcome | Data Collection | Date(s) |
| Students will earn at least $300 through a fundraiser. (Funds to be used for more consumable items such as photo paper, printer cartridges, etc.) | ITC and computer teacher calculate profits through fundraiser sales. | Feb. 17, 2010 May 7, 2010 |

Budget

In order to complete our grant activities we will need a digital camera that also can record short videos and a memory stick for mass storage. We will also need photo, magnet, and sticker paper that will be used for the educational posters and also for our fundraisers. Lastly, we will need color cartridges for our laser printer. All products will be purchased at Office Depot. All purchases will be initiated by the computer teacher, Ms. Hayes, and all funding will be monitored by the school bookkeeper, Kim Nall.  The specific breakdown is listed below and is also submitted as an Excel file.

| GRANT BUDGET |  |  |  |
| --- | --- | --- | --- |
| PRODUCT | PRICE | QUANTITY | COST |
| Kodak® Photo Paper, Matte, 8 1/2" x 11", 39 Lb, Pack Of 100 Sheets | $ 16.99 | 5 | $ 84.95 |
| Sony® Cyber-shot® DSC-W220 12.1-Megapixel Digital Camera, Silver | $ 159.99 | 1 | $ 159.99 |
| Lexar™ Memory Stick Pro Duo™ Platinum II Memory Card, 4GB | $ 34.99 | 1 | $ 34.99 |
| Avery® Magnet Sheets 3270, 8-1/2" x 11", White, Pack of 5 | $ 14.00 | 3 | $ 42.00 |
| Top of Form Avery® Sticker Project Paper 4383, 8-1/2" x 11", Clear, Pack of 10 Bottom of Form | $ 13.60 | 2 | $ 27.20 |
| Top of Form Media Sciences® MSI300CMYK Color/Black Laser Toner Cartridges, Pack Of 4 Bottom of Form | $ 139.99 | 1 | $ 139.99 |
| TOTAL COST OF GRANT PROJECT |  |  | $ 489.12 |