School Improvement Action Plan Using Technology

Kristen Honaker

November 11, 2009

Introduction

The Houston County Crossroads Center is located in Warner Robins, Georgia. It was built in 1946 and is the oldest school building in the district. In 2000, the building was designated to house Houston County’s alternative school. The school serves as a temporary alternate education route for those middle and high school students who have been suspended from their home schools.  All of the teachers are highly qualified in their respective areas, and many are at-risk certified. We are committed to providing a safe, educational environment for students until they are permitted to return to their home schools.  The school population changes from grading period to grading period and generally includes a large number of students who receive special education services. One of our biggest challenges is to engage our at-risk students so that they will become and stay more academically motivated. This year we are hoping to reduce the number of discipline referrals by 5% and decrease the number of student absences by 3%. Our school system has recently placed an emphasis on using more technology in the classroom, and we think incorporating more regular use of technology will assist us with achieving our school goals.

Technology Concerns

The SMART Boards are an excellent way to engage the students, increasing interest level in the lessons. The school system supports and promotes the use of interactive whiteboards throughout the county and is currently working on a plan to provide all schools with additional interactive boards. It is an outstanding way to incorporate technology into the classroom, as required by our county goals. Crossroads is fortunate enough to already have two SMART Boards in the building.  One of the boards is mounted in the media center. Another board is located in the Read 180 classroom. The school has already purchased two more SMART Boards with recently obtained funds from the county.

After observing the sign up calendar for the SMART Boards for the 2008-2009 school year, we have ascertained that the SMART Boards are only being used approximately 15% of the time it is available. During that time, the boards are only being used by 4 of the 25 teachers in the school. Our concern is that we have invested in expensive equipment that helps us motivate students as well as meet county technology goals but is not being utilized like it could be. In order to change, this we had to find out why there seemed to be such little interest in the SMART Boards.

The teachers were surveyed about their use of available SMART Boards. We found that 86% of the teachers did not feel qualified or comfortable enough to use the boards. Fifty-five percent said that the location of the SMART Board was inconvenient.   Sixty-seven percent of teachers said they did not feel they had enough time to prepare lessons to be used with the interactive whiteboards. Approximately 10% of the staff had no training on the SMART Board. The good news is that 100% of the teachers are willing to use the board if they receive additional training and assistance.

After analyzing the survey results about the use of the interactive whiteboards and speaking with the faculty, it appears that the number one concern is lack of training and/or comfort level with using the SMART Boards. In order to increase the use of the interactive boards, it is apparent that the staff needs to receive training in order to increase their level of comfort in using the boards as well as and receive additional support when putting their knowledge into practice.  Several teachers also pointed out that it would be helpful if there were a collection of lessons that were prepared and ready for the teachers to use.

POSSIBLE SOLUTIONS

How can we get the teachers to use the SMART Board with their students more often? Some possible solutions include having a SMART representative train the staff, having teachers who are comfortable with the boards train other teachers, and having the instructional technology coordinator train the teachers and provide support during instructional time. It may also be possible for teachers to take professional learning classed offered by the county throughout the year. In addition, we could try to purchase, create, and share a collection of lessons to help cut down on teacher preparation time.

A SMART certified trainer would charge approximately $995/per person for initial SMART certification. This would also likely take place during the school day and would require additional money for substitutes and possibly travel charges. The county staff development classes for SMART training are only offered in February this school year and are limited to only twelve participants for the entire county. The logical and least expensive choice seems to be to have our instructional technology coordinator conduct training on the SMART Board with all teachers. She will get re-certified through a SMART Trainer on the latest version of SMART Notebook software. Afterward, she will assist teachers with their SMART Board lessons in the classroom.  The principal has agreed that the teachers can use an entire professional learning day devoted to creating SMART Board lessons. The professional learning day will be conducted by the instructional technology coordinator.

In addition, it has been determined that one of the new SMART Boards will be mounted in an empty classroom, and the second one will be portable for the entirety of the school year. The classroom will have a rotating schedule for all teachers to use, as will the one in the media center. The portable one can be checked out by any of the teachers but will be mostly set aside for the instructional technology coordinator when she is assisting beginning teachers. It is our hope that this will make the process easier on the teachers. The technology coordinator will be responsible for setting up the SMART Board in the teacher’s room that day (all rooms are already outfitted with projectors). She will also either model or assist the teacher with lessons using the SMART Board through the day. All instructional technology coordinator and other personnel responsibilities are listed below in the action plan.

ACTION PLAN

Technology goal: All teachers use the SMART Boards with their students on a regular, rotating basis throughout the school year.

| Action Steps/Activities | Timeline | Person Responsible |
| --- | --- | --- |
| ITC re-certified as SMART trainer | November 19, 2009 | ITC |
| 2 additional SMART Boards tentative arrival | November 22-29, 2009 | Southern Business Co.; ITC to follow up |
| SMART Board mounted in designated room; other SMART Board assembled | December 1-4, 2009 | School system maintenance |
| Staff training after school hours 4 days | December 9-10, 2009 December 16-17, 2009 | ITC |
| Create lessons during professional learning day | January 4, 2010 | Teachers, ITC |
| Create rotating schedule for media center and dedicated SMART Board room | January 4, 2010 | ITC |
| Create sign up for portable Board | January 4, 2010 | ITC |
| Create 2 additional lessons for each academic area | January 4-9, 2010 | ITC |
| Review SMART Board basics during teacher planning | January 5, 2010 | ITC |
| Assist teachers with modeling and incorporating SMART lessons | January 11-March 10, 2010 **supported provided beyond March 10 if needed | ITC, teachers |
| Evaluation and discussion about SMART implementation during teacher planning; Gather ideas for next school year | March 10, 2010 | ITC, teachers |

BUDGET

The cost of implementing our SMART Board plan is shown below. By utilizing the ITC and scheduled work time, we are able to make this plan very cost-effective.

| ACTIVITY | COST |
| --- | --- |
| ITC re-certified for SMART | $875.00 |
| Travel expenses for re-certification |  |
| Hotel | $129.00 |
| Gas | $67.25 |
| After school training (ITC payment - 10 hours) | $400.00 |
| TOTAL | $1,471.25 |
| **2 additional SMART Boards previously purchased ($2678.09) |  |

SUMMARY

Crossroads will be fortunate enough to have four SMART Boards in their building by the end of December 2009. Because we believe that the SMART Boards are an effective way to incorporate technology into the classroom lessons, we plan to provide thorough training and support for all teachers.  After the instructional technology coordinator is re-certified by SMART she will do ten hours of training with the teachers. After completing the ten hours, the teachers will be SMART certified. The coordinator will continue to provide support by modeling and assisting with lessons throughout the school year. To ensure the SMART boards are being used to their maximum potential, a rotating schedule will be created for two of the SMART Boards. The SMART Board in the Read 180 room will continue to be used by the two teachers who have class in that room. The SMART Board in the media center will be available for teachers to sign up. A professional learning day will be set aside to allow teachers to create lessons, and the coordinator will make additional lessons available to the teachers. On March 10th, teachers will meet with the coordinator to discuss, progress, concerns and suggestions for the next school year.